## Work Breakdown Structure
WBS ID | Task Name | Task Description | Parent Task | Est. Days | Start Date | End Date | Dependencies | Assigned To | Status
1 | Project Initiation & Planning | Define project scope, objectives, and requirements | None | 10 | 2026-06-22 | 2026-07-01 | None | Vezinduna | In Progress
1.1 | Stakeholder Analysis | Identify stakeholders and their needs | 1 | 2 | 2026-06-22 | 2026-06-23 | None | Vezinduna | Not Started
1.2 | Requirements Gathering | Gather functional and non-functional requirements | 1 | 4 | 2026-06-24 | 2026-06-27 | 1.1 | Vezinduna | Not Started
1.3 | Create SRS Document | Document requirements and system specifications | 1 | 3 | 2026-06-28 | 2026-06-30 | 1.2 | Vezinduna | Not Started
1.4 | Requirements Sign-Off | Review and finalize requirements | 1 | 1 | 2026-07-01 | 2026-07-01 | 1.3 | Vezinduna | Not Started
2 | System Design | Design architecture, database, and UI | None | 21 | 2026-07-02 | 2026-07-24 | 1.4 | Vezinduna | Not Started
2.1 | Architecture Design | Design system architecture and components | 2 | 4 | 2026-07-02 | 2026-07-07 | 1.4 | Vezinduna | Not Started
2.2 | Database Design | Design ERD and database schema | 2 | 4 | 2026-07-08 | 2026-07-11 | 2.1 | Vezinduna | Not Started
2.3 | UI/UX Design | Create wireframes and dashboard layouts | 2 | 4 | 2026-07-12 | 2026-07-15 | 2.1 | Vezinduna | Not Started
2.4 | UML Diagrams | Develop Use Case, Class, Sequence, and Activity diagrams | 2 | 5 | 2026-07-16 | 2026-07-20 | 2.2 | Vezinduna | Not Started
2.5 | Design Review | Validate and finalize design artifacts | 2 | 4 | 2026-07-21 | 2026-07-24 | 2.3 | Vezinduna | Not Started
3 | Core Development | Build all system functionality | None | 36 | 2026-07-25 | 2026-09-11 | 2.5 | Vezinduna | Not Started
3.1 | Database Implementation | Create tables, constraints, and relationships | 3 | 4 | 2026-07-25 | 2026-07-30 | 2.5 | Vezinduna | Not Started
3.2 | Inventory Management Module | Add, edit, delete, categorize inventory items | 3 | 6 | 2026-07-31 | 2026-08-07 | 3.1 | Vezinduna | Not Started
3.3 | Storage Compatibility Engine | Implement chemical/biological safety rules | 3 | 6 | 2026-08-08 | 2026-08-15 | 3.2 | Vezinduna | Not Started
3.4 | Inventory Tracking Module | Track stock movement and usage | 3 | 5 | 2026-08-16 | 2026-08-22 | 3.2 | Vezinduna | Not Started
3.5 | Expiry & Degradation Monitoring | Implement alerts and monitoring logic | 3 | 4 | 2026-08-23 | 2026-08-28 | 3.4 | Vezinduna | Not Started
3.6 | Predictive Analytics Module | Forecast consumption and shortages | 3 | 5 | 2026-08-29 | 2026-09-04 | 3.4 | Vezinduna | Not Started
3.7 | Dashboard & Visualizations | Build dashboard and storage relationship views | 3 | 4 | 2026-09-05 | 2026-09-09 | 3.5 | Vezinduna | Not Started
3.8 | Search & Notifications | Implement search, filtering, and alerts | 3 | 2 | 2026-09-10 | 2026-09-11 | 3.7 | Vezinduna | Not Started
4 | Testing & Quality Assurance | Verify system functionality and quality | None | 19 | 2026-09-12 | 2026-10-02 | 3.8 | Vezinduna | Not Started
4.1 | Unit Testing | Test individual components and modules | 4 | 6 | 2026-09-12 | 2026-09-18 | 3.8 | Vezinduna | Not Started
4.2 | Integration Testing | Verify interactions between modules | 4 | 5 | 2026-09-19 | 2026-09-24 | 4.1 | Vezinduna | Not Started
4.3 | System Testing | Perform end-to-end testing | 4 | 4 | 2026-09-25 | 2026-09-28 | 4.2 | Vezinduna | Not Started
4.4 | Bug Fixing & Optimization | Resolve defects and improve performance | 4 | 4 | 2026-09-29 | 2026-10-02 | 4.3 | Vezinduna | Not Started
5 | Deployment & Portfolio Preparation | Prepare project for demonstration and showcase | None | 13 | 2026-10-03 | 2026-10-15 | 4.4 | Vezinduna | Not Started
5.1 | User Documentation | Create user guide and installation guide | 5 | 4 | 2026-10-03 | 2026-10-06 | 4.4 | Vezinduna | Not Started
5.2 | Deployment Setup | Configure database and deployment environment | 5 | 3 | 2026-10-07 | 2026-10-09 | 5.1 | Vezinduna | Not Started
5.3 | Portfolio Assets | Create screenshots, diagrams, and demo video | 5 | 3 | 2026-10-10 | 2026-10-12 | 5.2 | Vezinduna | Not Started
5.4 | Final Review & Handover | Final project review and submission | 5 | 3 | 2026-10-13 | 2026-10-15 | 5.3 | Vezinduna | Not Started